## Risk Checklist
[7 empty] | Exposure to Risk |  | Impact
[9 empty] | VL | L | M | H | VH
[7 empty] | Probability | VH | 2 | 2 | 0 | 1 | 0
[8 empty] | H | 2 | 2 | 4 | 0 | 0
[8 empty] | M | 0 | 0 | 0 | 1 | 2
[8 empty] | L | 0 | 0 | 1 | 1 | 1
[8 empty] | VL | 0 | 2 | 0 | 1 | 0
Category | Sub Category | Description | ID | At Risk | Risk Contents | Alleviation Plan | Planned Completion Date | Confirmation Date | Person in Charge | Probability | Impact | Exposure to Risk | Priority | P*C | P | C | C | P
Development Stage | Requirements Analysis | Requirement Change Probability | A1.1 | Y | Requirement change when team doing project | Accept changes and modified plan | 17/03/2013 |  | Team | VH | L | Medium | 17 | 20 | 5 | 2 | L | VH | - | re12 | - | - | - | Medium | 2
|  |  | A1.1 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Missing requirements | A1.2 | Y | Miss some requirements about SW capacity, performance | Add requirement to plan. Add task. | 17/03/2013 |  | Hung | VL | L | Low | 18 | 2 | 1 | 2 | L | VL | - | - | - | - | re52 | Low | 1
|  |  | A1.2 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Incorrect (non-confirmed) requirements | A1.3 | Y | Because this is the first team team working on this kind of project, so many mis-understanding and incorrect design is unavoidable | Redesign project and adopt to new plan | 17/03/2013 |  | Minh | H | M | Medium | 16 | 24 | 4 | 3 | M | H | - | re23 | - | - | - | Medium | 2
|  |  | A1.3 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Failure of preparing the SD card | A1.4 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | A1.4 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Requirements requiring the application of new technology | A1.5 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | A1.5 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
| Design and Implementation | Performance related issue | A2.1 | Y | Change song take too long: >2s | Check file system and DSP module. Optimize processing. | 24/03/2013 |  | Phong, Minh | M | H | Medium | 14 | 24 | 3 | 4 | H | M | - | - | re34 | - | - | Medium | 2
|  |  | A2.1 | Y | Button response take too long: >100 ms | Check interupt routine. Optimize processing. | 24/03/2013 |  | Hung | L | VH | Medium | 15 | 20 | 2 | 5 | VH | L | - | - | re45 | - | - | Medium | 2
|  |  | A2.1 | Y | Radio Internet function play music not smooth because of the Ethernet environment | Check the Ethernet environment | 24/03/2013 |  | Minh | L | H | Medium | 13 | 16 | 2 | 4 | H | L | - | - | re44 | - | - | Medium | 2
|  |  | A2.1 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Hardware restrictions (speed, capacity, reliability…) are not considered | A2.2 | Y | Hardware incompatible: Codec board not suitable | Research for problem. Recheck the electric circuits. Find another board | 17/03/2013 |  | Minh | M | VH | High | 1 | 45 | 3 | 5 | VH | M | re35 |  |  |  |  | High | 3
|  |  | A2.2 | Y | Problem with board LM3S6965 | Ask teacher for permission to test and fix. Change board component if needed. | 17/03/2013 |  | Phong | VL | H | Low | 19 | 4 | 1 | 4 | H | VL | - | - | - | - | re54 | Low | 1
|  |  | A2.2 | Y | Lack of button | Arrange button, set new function to button like press and hold | 17/03/2013 |  | Minh | H | VL | Low | 21 | 4 | 4 | 1 | VL | H | - | - | - | re21 | - | Low | 1
|  | Failure of dealing with Hardware changes (application of a new chip, change of tuner or sub micom, etc.) | A2.3 | Y | Change board | Write code in module, so that if changes happen, we can reuse code will less pain. | 15/04/2013 |  | Team | VL | L | Low | 20 | 2 | 1 | 2 | L | VL | - | - | - | - | re52 | Low | 1
|  |  | A2.3 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | OS resource management problem | A2.4 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | A2.4 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Not developed software (legacy code and vendor's code) related issue | A2.5 | Y | Sample decode and codec code not work | Find another sample code. Research for the reason and modifiy code to make it work. | 17/03/2013 |  | Minh | M | VH | High | 2 | 45 | 3 | 5 | VH | M | re35 |  |  |  |  | High | 3
|  |  | A2.5 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Implementation restrictions or issues | A2.6 | Y | No electricity when change place of development environment | Use laptop battery power. | 15/04/2013 |  | Team | H | VL | Low | 22 | 4 | 4 | 1 | VL | H | - | - | - | re21 | - | Low | 1
|  |  | A2.6 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Issues for the security design and implementation | A2.7 | N | [7 empty] | 0
|  |  | A2.7 | N | [7 empty] | 0
| Test | The test cannnot be performed or the evaluation method is insufficient | A3.1 | Y | Difficult when testing data transfering between LM3S6965 and VS1011 board | User terminal with UART connection | 15/04/2013 |  | Minh | H | M | Medium | 11 | 24 | 4 | 3 | M | H | - | re23 | - | - | - | Medium | 2
|  |  | A3.1 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | The system test is not performed | A3.2 | Y | Lack of board | Borrow board from other group | 15/04/2013 |  | Team | H | M | Medium | 10 | 24 | 4 | 3 | M | H | - | re23 | - | - | - | Medium | 2
|  |  | A3.2 | Y | We just have 1 board VS1011, so the team member may not allway have board to test | Arrange time effeciently. Test module by module | 15/04/2014 |  | Team | H | L | Medium | 12 | 16 | 4 | 2 | L | H | - | re22 | - | - | - | Medium | 2
|  | The field test schedule is not determined | A3.3 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | A3.3 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
| Etc. | External certification method or schedule problem | A4.1 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | A4.1 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Difficulty with the safety check | A4.2 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | A4.2 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Difficulty in securing compatibility | A4.3 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | A4.3 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Degradation of usability | A4.4 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | A4.4 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Specifications observation related issues (e.g. preparing for countries where the DTV specifications have not been confirmed.) | A4.5 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | A4.5 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Insufficient preliminary review | A4.6 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | A4.6 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | External certification method or schedule problem | A4.7 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | A4.7 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
Development Environment | Tools and Environment | No development support tool | B1.1 | Y | Keil ARM evaluation version cannot compile large project | Use a temporary key | 24/04 |  | Team | VH | VL | Low | 22 | 5 | 5 | 1 | VL | VH | - | - | - | re11 | - | Low | 1
|  |  | B1.1 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Insufficient training of development support tools | B1.2 | Y | Meet difficulties with compiling code in Keil | Ash teacher for help in lab time: Friday afternoon. | 24/03/2013 |  | Team | L | M | Low | 23 | 6 | 2 | 3 | M | L | - | re43 | - | - | - | Low | 1
|  |  | B1.2 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Communication problems between organizations, overseas laboratories and outsourcing vendors | B1.3 | Y | Can contact team's member when needed | Keep contact by email. User cell phone. |  |  | Team | H | L | Medium | 8 | 16 | 4 | 2 | L | H | - | re22 | - | - | - | Medium | 2
|  |  | B1.3 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
Project Management Side | Management Process | Problems with the schedule | C1.1 | Y | The development term is quirte short - investigate new tool, new technique and code. | Start research right from week 2 | 17/03/2013 |  | Team | VH | VL | Low | 24 | 5 | 5 | 1 | VL | VH | - | - | - | re11 | - | Low | 1
|  |  | C1.1 | Y | A schedule delay. | Check progress twice a week. Other members help when one member delay schedule | 31/03/2013 |  | Team | VH | H | High | 3 | 60 | 5 | 4 | H | VH | re14 |  |  |  |  | High | 3
|  | Insufficient experience of the manager in software development and management | C1.2 | Y | No experience of project management | Learn ourselves Get helps and guidances from teacher | 24/03/2013 |  | Team | VH | L | Medium | 9 | 20 | 5 | 2 | L | VH | - | re12 | - | - | - | Medium | 2
|  |  | C1.2 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
| Management Methods | Not having configuration management procedures and tools | C2.1 | Y | Cooperate not good between team member because we have to work apart | Arrange time to work together at C5 laboratory. Communicate by Skype for any question or concern | 24/03/2013 |  | Team | H | M | Medium | 7 | 24 | 4 | 3 | M | H | - | re23 | - | - | - | Medium | 2
|  |  | C2.1 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
| Overseas and Outsourcing Development | Failure to observe the due date of an overseas laboratory or oursourcing vendor | C3.1 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | C3.1 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | A quality problem with the product developed by an overseas laboratory or oursourcing vendor | C3.2 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | C3.2 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Dependancy on the product or service developed by an overseas laboratory or oursourcing vendor | C3.3 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | C3.3 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | A technology transfer problem of the outsourced development | C3.4 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | C3.4 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Insufficient experience in outsourcing development management | C3.5 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | C3.5 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
| Resources | Insufficient human resources for development | C4.1 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | C4.1 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Problems with the stability and maintenance of human resources | C4.2 | Y | Team member are busy with other subject and project | Make appointment to work together 2 times a week. Set task for member can work at home. | 24/03/2013 |  | Team | VH | M | High | 4 | 45 | 5 | 3 | M | VH | re13 |  |  |  |  | High | 3
|  |  | C4.2 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Insufficient human resources for the system test | C4.3 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | C4.3 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Insufficient technical ability and experience of human resources | C4.4 | Y | Some member may not very good at coding with Microcontroller and ARM architect. | Learn ourselves. Team member help each other. Get helps and guidances from teacher | 2013-02-03 |  | Team | VH | M | High | 5 | 45 | 5 | 3 | M | VH | re13 |  |  |  |  | High | 3
|  |  | C4.4 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Insufficient knowledge of the function of the evaluator | C4.5 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | C4.5 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
| Etc. | Project coverage changes | C5.1 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | C5.1 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Integration or cancellation of the project | C5.2 | Y | Cancel project | Cancel project and prepare for next project | 24/03/2013 |  | Team | VL | VH | Medium | 6 | 10 | 1 | 5 | VH | VL | - | - | - | - | re55 | Medium | 2
|  |  | C5.2 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Dependency on other projects | C5.3 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | C5.3 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | Security problems due to externally stationed staff members | C5.4 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | C5.4 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  | (RLC) intellectual property rights or patents rights infringement | C5.5 | Y | Patents and source code copyright | For academic purpose, we will accept of using those patents and source code | 24/03/2013 |  | Team | H | VL | Low | 25 | 4 | 4 | 1 | VL | H | - | - | - | re21 | - | Low | 1
|  | (RLC) Analysis and result management of 'the intellectual property rights and patent' | C5.6 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
User-Defined Risk |  | Copyright problem | D1.1 | Y | Patents and source code copyright | For academic purpose, we will accept of using those patents and source code | 24/03/2013 |  | Team | H | VL | Low | 26 | 4 | 4 | 1 | VL | H | - | - | - | re21 | - | Low | 1
|  | Financial problem | D1.2 | Y | Lack money to buy new board | Team member contribute | 2013-03-03 |  | Team | M | VL | Low | 27 | 3 | 3 | 1 | VL | M | - | - | - | re31 | - | Low | 1
|  |  | D1.3 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | D1.4 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | D1.5 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | D1.6 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | D1.7 | N | [9 empty] | 0 |  |  |  |  | - | - | - | - | -
|  |  | D1.8 | N
A risk item that was not found when planning the development but actually threatened the project (Create this after the development completion and attach it to the SDC.) |  |  | E1.1 | Y | Error SD card | Test on a new SD card | 24/03/2013 |  | Team | VL | H | Low | 28
|  |  | E1.2 | N
|  |  | E1.3 | N
|  |  | E1.4 | N
|  |  | E1.5 | N
|  |  | E1.6 | N
|  |  | E1.7 | N
|  |  | E1.8 | N