## Barcode-WBS
Mplayer Project - Work Breakdown Structure/Schedule
|  |  | Planned |  | Actual |  | % | Show Gantt for | [5 empty] | Planned | [5 empty] | Show Status? |  |  |  |  | █ | What is current week? |  | 15
Part | # | List of Activties | Start | Dur | Start | Dur | Done | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
SW Planning | 1 | Software Requirement & Planning | 1 | 3 | 1 | 3 | 100% | █ | █ | █
| 2 | Setup Hardware | 2 | 1 | 2 | 1 | 100% |  | █
Investigation | 3 | Environement and Tool | 2 | 1 | 2 | 5 | 100% |  | █
| 4 | Module 1(File_System) | 3 | 2 | 3 | 2 | 100% |  |  | █ | █
| 5 | Module 2(Display) | 3 | 2 | 3 | 5 | 100% |  |  | █ | █
| 6 | Module 3(Controller) | 3 | 2 | 3 | 2 | 100% |  |  | █ | █
| 7 | Module 4 (Read file content) | 3 | 2 | 3 | 2 | 100% |  |  | █ | █
| 8 | Module 5(VS1011 Interface) | 3 | 4 | 3 | 4 | 100% |  |  | █ | █ | █ | █
| 9 | Module 6(http_streaming) | 3 | 2 | 3 | 4 | 100% |  |  | █ | █
Design | 10 | Function Design | 6 | 2 | 6 | 2 | 100% | [5 empty] | █ | █
| 11 | Module 1(File_System) | 7 | 2 | 7 | 2 | 100% | [6 empty] | █ | █
| 12 | Module 2(Display) | 7 | 3 | 7 | 3 | 100% | [6 empty] | █ | █ | █
| 13 | Module 3(Controller) | 7 | 2 | 7 | 2 | 100% | [6 empty] | █ | █
| 14 | Module 4 (Read file content) | 7 | 2 | 7 | 2 | 100% | [6 empty] | █ | █
| 15 | Module 5(VS1011 Interface) | 7 | 3 | 7 | 3 | 100% | [6 empty] | █ | █ | █
| 16 | Module 6(http_streaming) | 7 | 2 | 7 | 2 | 100% | [6 empty] | █ | █
Coding | 17 | Module 1(File_System) | 10 | 2 | 10 | 2 | 100% | [9 empty] | █ | █
| 18 | Module 2(Display) | 10 | 3 | 10 | 3 | 100% | [9 empty] | █ | █ | █
| 19 | Module 3(Controller) | 10 | 2 | 10 | 2 | 100% | [9 empty] | █ | █
| 20 | Module 4 (Read file content) | 10 | 2 | 10 | 2 | 100% | [9 empty] | █ | █
| 21 | Module 5(VS1011 Interface) | 10 | 3 | 10 | 3 | 100% | [9 empty] | █ | █ | █
| 22 | Module 6(http_streaming) | 10 | 2 | 10 | 2 | 100% | [9 empty] | █ | █
Testing | 23 | System Test Plan | 4 | 2 | 4 | 2 | 100% |  |  |  | █ | █
| 24 | System Test Design Testcase | 8 | 2 | 8 | 2 | 100% | [7 empty] | █ | █
| 25 | Unit Test | 12 | 2 | 12 | 2 | 100% | [11 empty] | █ | █
| 26 | System Test & Demo | 13 | 3 | 13 | 3 | 80% | [12 empty] | █ | █ | █
Release | 27 | Release | 16 | 1 | 0 | 0 | 0%
| 22 | Activity 22 | 0 | 0 | 0 | 0 | 0%
| 23 | Activity 23 | 0 | 0 | 0 | 0 | 0%
| 24 | Activity 24 | 0 | 0 | 0 | 0 | 0%
| 25 | Activity 25 | 0 | 0 | 0 | 0 | 0%
| 26 | Activity 26 | 0 | 0 | 0 | 0 | 0%
| 27 | Activity 27 | 0 | 0 | 0 | 0 | 0%
| 28 | Activity 28 | 0 | 0 | 0 | 0 | 0%
| 29 | Activity 29 | 0 | 0 | 0 | 0 | 0%
| 30 | Activity 30 | 0 | 0 | 0 | 0 | 0%
| 31 | Activity 31 | 0 | 0 | 0 | 0 | 0%
| 32 | Activity 32 | 0 | 0 | 0 | 0 | 0%
| 33 | Activity 33 | 0 | 0 | 0 | 0 | 0%
| 34 | Activity 34 | 0 | 0 | 0 | 0 | 0%
| 35 | Activity 35 | 0 | 0 | 0 | 0 | 0%
| 36 | Activity 36 | 0 | 0 | 0 | 0 | 0%
| 37 | Activity 37 | 0 | 0 | 0 | 0 | 0%
| 38 | Activity 38 | 0 | 0 | 0 | 0 | 0%
| 39 | Activity 39 | 0 | 0 | 0 | 0 | 0%
| 40 | Activity 40 | 0 | 0 | 0 | 0 | 0%
[8 empty] | 2013-02-25 |  |  |  | 2013-03-25 |  |  |  | 2013-04-25 |  |  |  | 2013-05-05 |  |  |  | 2013-05-20 |  |  | 2012-11-26
Note on O6: Mplayer: EA: - SW Requirements Specification - SW Development Plan - SW System Test Plan
Note on V6: Mplayer: ER1: - SW High Level Design - SW Detailed Level Design - SW System Test Design Report
Note on X6: Mplayer: CA: - SW System Test Result Report - SW Development Completion Report - Built Image and Demo guidance
Note on M7: Mplayer: PA

## Legend
Types of Gantt | Symbols to be used for % complete
Planned | █
Actual | ↓
•
Note on D6: This one lets you disable the completion status